## TargetWorkPlanPeriodic
Date | Target | Description | Remaining
Week 1 April | READ PAPERS | Read Generic Papers around llms, agentic ai, xai in 6g | Nothing
Week 2 April | READ PAPERS AND SOMEMath. COLLECT PAPERS FOR NAR. | Continue reading generic papers. Find some notes and books on geometric DL. (These are foundations for NAR). Collected the majority of papers that are about nar since its inception | Nothing
Week 3 April | READ PAPERS AND SOME Math. COLLECT PAPERS FOR NAR. Read up a bit on telecom | Continue with the papers. Focus a bit more on NAR this week to understand how it works. | Nothing
Week 4 April | Continue WITH PAPERS. DO SOME NAR CODING EXAMPLES. TRY TO CREATE SYSTEM MODELS FOR DASH PAPER | FOCUS ON NAR AND LESS ON GENERIC PAPERS. GATHER PAPERS SPECIFICALLY ON RECONFIGURATION TASK PLANNING (IN TELECOM AND ELSEWHERE). ORGANISE A BIT BETTER MY NOTES ON GEOMETRIC DL. IMPLEMENT NAR ON DJIKSTRA. CREATE 2-3 SYSTEM MODELS FOR DASH PAPER. | Implemented NAR on bellmand ford instead of djikstra so noth remaining.
Week 1 May | START PRESENTATION PREPARATION. CLARIFY DELIVERABLES. | Begin presentation work. Reorganise solution-paper material by problem, tools, formulations, metrics, and datasets; then shift to the agreed NAR tutorial, 20-paper summary deck, and 3-4 paper deep-dive structure. | Continue. (Wanted a few more NAR papers but had no time)
Week 2 May | PREPARE NAR TUTORIAL PRESENTATION | Read additional NAR papers used in the tutorial and build the tutorial slides, figures, and presenter notes. | Nothing
Week 3 May | CONTINUE PAPER SUMMARY PRESENTATION | Continue the 20-paper summary presentation and organize the 3-4 paper deep-dive selection. Cover more NAR papers if time permits. | Continue
Week 4 May | UPDATE NAR TUTORIAL AND PAPER SUMMARY DECK | Make minor NAR tutorial updates for the next meeting and continue the mini-survey/paper-summary deck. | Continue
Week 1 Jun | REORGANISE PAPER SUMMARY DECK | Rework the paper-summary deck by solution area, with stronger edge/cloud focus and less overlap with LLM/O-RAN-only papers. Use detailed cards for system model, formulation, metrics, datasets, and results. | Continue
Week 2 Jun | PAUSE PRESENTATION; IMPLEMENT LMF LOCALIZATION CODE | Focus on the LMF localization problem. Implement synthetic graph/data generation, uncertainty-aware path selection, and baselines. | Continue
Week 3 Jun | CONTINUE LMF IMPLEMENTATION AND ATHENS EVALUATION | Finalize sigma/Cell-ID model and build the Athens OpenCelliD evaluation with distance/angle reliability metrics. | Continue
Week 4 Jun | WRITE LMF LOCALIZATION PAPER | Finish implementation/evaluation figures and write the conference paper draft for feedback. | Feedback pending
Week 1 Jul | GET FEEDBACK/FIX CONFERENCE PAPER, FINISH SUMMARY, START JOURNAL SEARCH | Get feedback and fix the conference paper. Finish the Phase 1 paper-summary deck (about 90% done), fix the small layout issue, and start looking for papers for the journal direction: multi-path fusion, randomized/scalable path direction maybe, and 1-2 relevant NAR papers. | Fix paper after feedback; finish deck
Week 2 Jul | READ AND SURVEY PAPERS | Full week dedicated to reading. Read background/related work on Digital Twins, spectrum allocation, and prediction to firm up the problem statement (Jul 8-9), then survey the collected papers one by one (Jul 9-14) to prepare material for the write-up. | Start writing the surveyed-papers section
Week 3 Jul | WRITE SURVEYED PAPERS SECTION; UPDATE ARCHITECTURE | Write the surveyed-papers section based on last week's reading (Jul 13-17). Once a solid draft exists, update the proposed architecture and necessary supporting text (Jul 16-20), then start the Network Digital Twins discussion for Section D (from Jul 20). | Finish Network Digital Twins discussion; move to manuscript polishing
Week 4 Jul | FINISH SECTION D; POLISH MANUSCRIPT; TRANSFER TO LATEX | Finish the Network Digital Twins discussion (through Jul 21), insert extra sentences throughout the manuscript in the relevant parts (Jul 21-22), then transfer all subsections into the LaTeX document (Jul 22-23). Remainder of the week: review full draft. | Continue journal work
Aug Week 1 | BREAK | Break. Optional light NAR reading/coding | Break
Aug Week 2 | BREAK | Break. | Break
Aug Week 3 | BREAK | Break. | Break
Aug Week 4 | RESUME JOURNAL WORK AND START WRITING | Finish remaining journal-related coding/results. Align with prof on corrections/direction and start writing the paper, writing may reveal extra experiments or papers needed (???). | Continue writing/corrections

## Output
Date | Details | Remaining | Comments
April Week 1 | ? P. Barnard, I. Macaluso, N. Marchetti and L. A. DaSilva, "Resource Reservation in Sliced Networks: An Explainable Artificial Intelligence (XAI) Approach," ICC 2022 - IEEE International Conference on Communications, Seoul, Korea, Republic of, 2022, pp. 1530-1535, doi: 10.1109/ICC45855.2022.9838766.? S. Ben Saad, B. Brik and A. Ksentini, "A Trust and Explainable Federated Deep Learning Framework in Zero Touch B5G Networks," GLOBECOM 2022 - 2022 IEEE Global Communications Conference, Rio de Janeiro, Brazil, 2022, pp. 1037-1042, doi: 10.1109/GLOBECOM48099.2022.10001371.? X. Cao et al., "Advancing LLM-Based Security Automation With Customized Group Relative Policy Optimization for Zero-Touch Networks," in IEEE Journal on Selected Areas in Communications, vol. 44, pp. 2669-2686, 2026, doi: 10.1109/JSAC.2025.3643844.? S. Chatzimiltis, M. B. Mashhadi, M. Shojafar, M. Debbah and R. Tafazolli, "Agentic AI for 6G: A New Paradigm for Autonomous RAN Security Compliance," arXiv:2512.12400, 2025, doi: 10.48550/arXiv.2512.12400.? S. Chatzimiltis, M. Shojafar, M. B. Mashhadi and R. Tafazolli, "AI-on-RAN for Cyber Defense: An XAI-LLM Framework for Interpretable Anomaly Detection," in IEEE Transactions on Network Science and Engineering, vol. 13, pp. 3301-3319, 2026, doi: 10.1109/TNSE.2025.3629983.? L. N. DeLong, R. F. Mir and J. D. Fleuriot, "Neurosymbolic AI for Reasoning Over Knowledge Graphs: A Survey," in IEEE Transactions on Neural Networks and Learning Systems, vol. 36, no. 5, pp. 7822-7842, May 2025, doi: 10.1109/TNNLS.2024.3420218. | Nothing
April Week 2 | ? L. Hong, S. Pan, F. Feng and C. Jiao, "Collaborative Communication for Edge LLM Servicing in Adversarial Networks: An MARL-Empowered Stackelberg Game Approach," in IEEE Internet of Things Journal, vol. 12, no. 20, pp. 41309-41317, 15 Oct. 2025, doi: 10.1109/JIOT.2025.3583280.? N. Khan, A. Abdallah, A. Celik, A. M. Eltawil and S. Coleri Ergen, "Explainable AI-Aided Feature Selection and Model Reduction for DRL-Based V2X Resource Allocation," in IEEE Transactions on Communications, vol. 73, no. 9, pp. 7633-7649, Sept. 2025, doi: 10.1109/TCOMM.2025.3554655.? W. Li, F. Tang, M. Zhao, M. Omachi and N. Kato, "Adaptive Large Language Model for Task Orchestration in 6G Space-Air-Ground Integrated Computing Power Networks," in IEEE Transactions on Network Science and Engineering, vol. 13, pp. 4847-4862, 2026, doi: 10.1109/TNSE.2025.3644352.? Y. Liu et al., "LAMeTA: Intent-Aware Agentic Network Optimization via a Large AI Model-Empowered Two-Stage Approach," in IEEE Journal on Selected Areas in Communications, vol. 44, pp. 2462-2478, 2026, doi: 10.1109/JSAC.2025.3642840.? C. Mawela, C. B. Issaid and M. Bennis, "A Web-Based Solution for Federated Learning With LLM-Based Automation," in IEEE Internet of Things Journal, vol. 12, no. 12, pp. 19488-19503, 15 Jun. 2025, doi: 10.1109/JIOT.2025.3542897. IEEE Index Terms: Distributed computing; federated learning (FL); intent-based automation; large language models (LLMs); web sockets communication.? Read slides 1-3 on NAR (https://algo-reasoning.github.io/artefacts/) and collected papers for further reading.? Watched the slides video: https://www.youtube.com/watch?v=SKQ96tDZhgw.? Read slides/watched video for Theoretical Foundations of Graph Neural Networks (https://www.youtube.com/watch?v=uF53xsT7mjc).? Cloned the CLRS DeepMind repo (https://github.com/google-deepmind/clrs) to understand how NAR works in practice.? M. S. Munir et al., "Neuro-Symbolic Explainable Artificial Intelligence Twin for Zero-Touch IoE in Wireless Network," in IEEE Internet of Things Journal, vol. 10, no. 24, pp. 22451-22468, 15 Dec. 2023, doi: 10.1109/JIOT.2023.3303713. | Nothing
April Week 3 | ? Foundations of GNN (https://www.youtube.com/watch?v=uF53xsT7mjc).? Read Ch. 1 of Introduction to 5G by Christopher Cox.? Experimented with NAR on the Bellman-Ford algorithm (code).? Delved deeper into NAR: https://www.youtube.com/watch?v=KKGcXhT-E88.? Read two NAR papers: Neural Algorithmic Reasoning; Neural Execution of Graph Algorithms.? A. M. Nazar, A. Celik, M. Y. Selim, A. Abdallah, D. Qiao and A. M. Eltawil, "ENWAR 2.0: An Agentic Multimodal Wireless LLM Framework with Reasoning, Situation-Aware Explainability and Beam Tracking," in IEEE Transactions on Mobile Computing, pp. 1-18, 2025, doi: 10.1109/TMC.2025.3629736.? B. Picano, D. T. Hoang and D. N. Nguyen, "A Matching Game for LLM Layer Deployment in Heterogeneous Edge Networks," in IEEE Open Journal of the Communications Society, vol. 6, pp. 3795-3805, 2025, doi: 10.1109/OJCOMS.2025.3561605.? F. Rezazadeh, H. Chergui and J. Mangues-Bafalluy, "Explanation-Guided Deep Reinforcement Learning for Trustworthy 6G RAN Slicing," 2023 IEEE International Conference on Communications Workshops (ICC Workshops), Rome, Italy, 2023, pp. 1026-1031, doi: 10.1109/ICCWorkshops57953.2023.10283684.? A. Terra, R. Inam, S. Baskaran, P. Batista, I. Burdick and E. Fersman, "Explainability Methods for Identifying Root-Cause of SLA Violation Prediction in 5G Network," GLOBECOM 2020 - 2020 IEEE Global Communications Conference, Taipei, Taiwan, 2020, pp. 1-7, doi: 10.1109/GLOBECOM42002.2020.9322496.? H. Zhou et al., "Large Language Model (LLM) for Telecommunications: A Comprehensive Survey on Principles, Key Techniques, and Opportunities," in IEEE Communications Surveys & Tutorials, vol. 27, no. 3, pp. 1955-2005, Jun. 2025, doi: 10.1109/COMST.2024.3465447.? Read NAR paper: Neural Execution of Graph Algorithms.? Read "To Dash or not to Dash" and started thinking about a possible extension; nothing concrete yet.? Read NAR paper on Pointer Graph Networks.
April Week 4 | ? J. Gilmer, S. S. Schoenholz, P. F. Riley, O. Vinyals and G. E. Dahl, "Neural Message Passing for Quantum Chemistry," ICML 2017, arXiv:1704.01212. ? F. Kavehmadavani, V.-D. Nguyen, T. X. Vu and S. Chatzinotas, "Intelligent Traffic Steering in Beyond 5G Open RAN Based on LSTM Traffic Prediction," in IEEE Transactions on Wireless Communications, vol. 22, no. 11, pp. 7727-7742, Nov. 2023, doi: 10.1109/TWC.2023.3254903. ? M. Gupta, S. Chinchali, P. P. Varkey and J. G. Andrews, "Forecaster-Aided User Association and Load Balancing in Multi-Band Mobile Networks," IEEE Transactions on Wireless Communications, vol. 23, no. 5, pp. 5157-5171, May 2024, doi: 10.1109/TWC.2023.3324685. ? X. Guo, F. Yan, X. Xue, B. Pan, G. Exarchakos and N. Calabretta, "QoS-aware data center network reconfiguration method based on deep reinforcement learning," Journal of Optical Communications and Networking, vol. 13, no. 5, pp. 94-107, May 2021, doi: 10.1364/JOCN.413188. ? L. Zanzi, V. Sciancalepore, A. Garcia-Saavedra, H. D. Schotten and X. Costa-Perez, "LACO: A Latency-Driven Network Slicing Orchestration in Beyond-5G Networks," arXiv:2009.03771v1, 7 Sept. 2020. ? J. Zhang, M. Ye, Z. Guo, C.-Y. Yen and H. J. Chao, "CFR-RL: Traffic Engineering with Reinforcement Learning in SDN," arXiv:2004.11986v1 [cs.NI], 24 Apr. 2020. ? S. Troia, R. Alvizu and G. Maier, "Reinforcement Learning for Service Function Chain Reconfiguration in NFV-SDN Metro-Core Optical Networks," IEEE Access, vol. 7, pp. 166444-166457, 2019, doi: 10.1109/ACCESS.2019.2953498. ? P. Velickovic and C. Blundell, "Neural Algorithmic Reasoning," Patterns, 2021, arXiv:2105.02761. ? P. Velickovic, R. Ying, M. Padovano, R. Hadsell and C. Blundell, "Neural Execution of Graph Algorithms," ICLR 2020, arXiv:1910.10593. ? A. Dudzik and P. Velickovic, "Graph Neural Networks are Dynamic Programmers," NeurIPS 2022, arXiv:2203.15544. ? P. Velickovic et al., "The CLRS Algorithmic Reasoning Benchmark," ICML 2022, PMLR 162, arXiv:2205.15659. | Nothing | Continued with older NAR/GNN papers and telecom solution papers around reconfiguration, traffic steering, slicing, and network optimization.
May Week 1 | ? Started presentation preparation. ? Initially misunderstood the deliverables: I thought the NAR presentation was a separate fourth presentation and not a tutorial-style deck. ? Drafted a solution-paper landscape deck categorizing papers by problem, tools, formulations, metrics, and datasets. ? Clarified the final deliverables: NAR tutorial, 20-paper summary presentation, and 3-4 paper deep-dive presentation. | Continue with NAR tutorial and paper-summary/deep-dive decks. | Some time was lost due to the initial misunderstanding, but the solution-paper categorization remains useful for the summary presentation.
May Week 2 | ? Prepared the NAR tutorial presentation. ? Read additional NAR papers used in the deck: A Generalist Neural Algorithmic Learner; Neural Algorithmic Reasoning with Causal Regularisation; Neural Algorithmic Reasoning for Combinatorial Optimisation; Primal-Dual Neural Algorithmic Reasoning; Learning to Configure Computer Networks with Neural Algorithmic Reasoning; GraphVeri: A NAR-based control plane verification framework for routing protocols. ? Built slides and presenter notes on alignment, CLRS-30, GNN processors, field progression, datasets, and networking applications. | Continue paper summary presentation. | Main focus was NAR tutorial slide creation and organization.
May Week 3 | ? Continued the paper-summary presentation and the 3-4 paper deep-dive planning. ? Reworked material toward paper-level summaries with problem, system model, formulation/tools, metrics, datasets, and results. ? Tried to keep some NAR reading in scope, but most time went to presentation structure. | Continue paper-summary deck and cover more NAR papers. | Need more AI/NAR reading once the presentation load becomes lighter.
May Week 4 | ? Made minor updates to the NAR tutorial for the next meeting. ? Continued the mini-survey/paper-summary deck and refined the included-paper list. ? Started moving from method-based grouping toward area/problem-based grouping. | Finalize paper selection and continue slide cleanup. | Still need to read more AI/NAR papers; most work this week was presentation organization.
Jun Week 1 | ? Continued the Phase 1 paper-summary deck. ? Reorganized the selection around solution areas, with more focus on edge/cloud orchestration, task offloading, service chains, reconfiguration, and planning. ? Reduced overlap with LLM-only and O-RAN-only papers and moved toward detailed cards for system model, formulation, metrics, datasets, and results. | Continue deck revision and verify paper summaries. | Content direction became clearer -> edge/cloud and reconfiguration should be central, avoid overusing generic LLM/O-RAN material.
Jun Week 2 | ? Paused the presentation work and focused on the LMF localization problem. ? Built LocEstim code for synthetic graph/data generation, sigma models, uncertainty-aware path selection, and baseline comparisons. ? Added documentation around accumulated path variance, sigma vs sigma^2, and dataset/query design. | Finalize sigma model and move from synthetic data to Athens OpenCelliD experiments. | Few papers read this week because the focus was implementation. Need to resume AI/NAR literature after the code stabilizes.
Jun Week 3 | ? Continued LocEstim implementation. ? Finalized Cell-ID/sigma modeling and built the Athens LTE/OpenCelliD experiment plan. ? Added experiments and metrics for min-uncertainty vs min-hop, global NRMSE, hop counts, joint distance-angle success, and region sensitivity. ? Started notes on randomized path-search directions for scalable/future journal work. | Finish evaluation plots and move results into the paper draft. | Implementation and evaluation took priority, more AI/NAR reading is still needed. I also want to some coding on AI/NAR (e.g. train sth that is non trivial)
Jun Week 4 | ? Finished the main implementation/evaluation pass for the LMF localization paper. ? Wrote the paper draft in LaTeX: introduction, system model, Dijkstra/min-variance formulation, Athens LTE evaluation, figures, and conclusion/future work. ? Generated the PDF/Overleaf package and sent/expected feedback. | Address feedback and polish the paper. | NAR/learned path selection is kept as future work, not as an implemented contribution.
Jul Week 1 | ? Finished the content of the Phase 1 paper deck remaining work is a small text-overflow fix, factual checking, and presentation preparation. ? Finished the LMF localization paper draft and expect feedback. ? Started journal-extension research on multi-path fusion, effective resistance, and scalable/randomized path ensembles. (Will wait to discuss if that is worth it though) Started reading P. Barooah and J. P. Hespanha, "Estimation on Graphs from Relative Measurements: Distributed Algorithms and Fundamental Limits," IEEE Control Systems Magazine, 2007. ? Read G. Rodionov and L. Prokhorenkova, "Discrete Neural Algorithmic Reasoning," arXiv:2402.11628, because the Dijkstra result may connect to the LMF/NAR direction. ? Started thinking about NAR/framework code for future learned path-selection experiments (probably after Aug). | Fix small deck layout issue, fact-check slides, prepare presentation, and wait for paper feedback. | Journal direction is still exploratory. the multi-path fusion survey/gap analysis is not fully read/explored/planned. Need more AI/NAR literature alongside the localization work for the future.
Jul Week 2
Jul Week 3
Jul Week 4
Aug Week 1
Aug Week 2
Aug Week 3
Aug Week 4